## Sheet1
Date (dd/mm/yyyy) | Employee(Merge your respective cells for your names) | Assigned Task(Dated from 10/06/2024) | Review Comments(Comments given on daily Basis) | Task Completion Status(% Completed) | Blockage | Ready for Review(Yes/No)
2024-06-12 | Amresh Kumar | 1. refactor code , 2. Push the new url's to excel 3. test the excel in bulk |  | 1st and 2nd Task- 100% Completed | 3rd Task (Response code errors) | Yes
| Aarush Kumar | Check for any existing hugging face transformer model to read the pdf files, go through vector database and RAG. Clean and add some comments to code for pdf extraction. |  | 100 | None | Yes
2024-06-13 | Amresh Kumar | Use pyppeteer for dynamic urls to get the Date, Authors, Title and Abstract
| Aarush Kumar | 1. Create GitHub account and a structured repo to push every day task and code. 2. Create a vector DB with pdf's, process the pdf and also the bulk of pdf's, implement RAG for finding results out in PDF answering to our queries like who's author, what is publication date & summary of doc, tweek pre-trained models, try on LoRA.